## Estimations
Epic | Story | Effort in hrs | Qunatity | Total Hours | Epic in Hours | Total in Hours
Setup Environment | Create NPID | 16 | 1 | 16
| Create Folder Structure | 16 | 1 | 16
| Create Github | 16 | 1 | 16
| Create Jenkins | 16 | 1 | 16
| Build Tomcat | 32 | 1 | 32 | 96
Crate MMP tables | Create Hbase main-history tables | 32 | 1 | 32
| Create Load scripts of Hbase tables | 32 | 1 | 32
| Create and Setup Scheduler job to load | 24 | 1 | 24 | 88
Create MMP POC Batch interface | POC- Create Hbase pattern table | 5 | 3 | 15
| POC- Create Load Script of Hbase table | 5 | 3 | 15
| POC- Create n Setup Scheduler job to load | 5 | 3 | 15
| POC- Develop Basic Pattern Request application | 32 | 1 | 32
| POC- Develop Match Patterns | 10 | 3 | 30
| POC- Develop Basic Pattern Response application | 30 | 1 | 30
| POC- Test Match Patterns | 12 | 1 | 12
| POC- Create n Setup Scheduler job to run application | 10 | 1 | 10 | 159
Create MMP POC RT interface | POC-RT- Develop API Spec for Req-Resp | 32 | 2 | 64
| POC-RT- Develop Basic REST Request application | 24 | 1 | 24
| POC-RT- Develop Match Patterns | 4 | 3 | 12
| POC-RT- Develop Basic REST Response application | 20 | 1 | 20
| POC-RT- Test Match Patterns | 12 | 1 | 12
| POC-RT- Create n Deploy webserver job to run REST application | 30 | 1 | 30 | 162
Create MMP Batch interface | Create Hbase pattern table | 3 | 15 | 45
| Create Load Script of Hbase table | 3 | 15 | 45
| Create n Setup Scheduler job to load | 3 | 15 | 45
| Develop Basic Pattern Request application | 20 | 1 | 20
| Develop Match Patterns | 8 | 15 | 120
| Develop Basic Pattern Response application | 20 | 1 | 20
| Test Match Patterns | 6 | 15 | 90
| Create n Setup Scheduler job to run application | 20 | 1 | 20 | 405
Create MMP RT interface | Develop API Spec for Req-Resp | 14 | 2 | 28
| Develop Basic REST Request application | 20 | 1 | 20
| Develop Match Patterns | 4 | 15 | 60
| Develop Basic REST Response application | 20 | 1 | 20
| Test Match Patterns | 4 | 15 | 60
| Create n Deploy webserver job to run REST application | 32 | 1 | 32 | 220
Support n Integrate MMP with Domain clients | Client: Develop client to invoke MMP Service | 32 | 1 | 32
| Support n Integrate with Domain teams | 12 | 3 | 36 | 68 | 1198